## VO No.2
Project : | BKT1, Bukit Tambun
Subcontractor :
Variation Order : 02 -
|  |  |  | VB Budget |  |  | QS |  |  | Sub-con Submission
Item | Description | BQ Ref. | Unit | Qty | Rate | Amount | Qty | Rate | Amount | Qty | Rate | Amount
Additional
Phase 1
Building
Prepare and apply one coat of sealer and two coats finishes weathershield to plastered surface to
1 | MS door to House Unit rear door | NEW | m2 | 257.04 | 7.37 | 1894.3848 | 257.04 | 5.5 | 1413.72 | 257.04 | 5.5 | 1413.72
Prepare and apply one coat of primer and two coats of general surfaces of metal door frame
2 | MS door frame to House Unit rear door | NEW | M | 346.8 | 2.86 | 991.848 | 346.8 | 3.8 | 1317.84 | 346.8 | 3.8 | 1317.84
Prepare and apply one coat of primer and two coats of general surfaces of metal door frame
3 | House unit cantilever roof | NEW | no | 68 | 33.3 | 2264.4 | 68 | 30 | 2040 | 68 | 30 | 2040
External Works
4 | Lay 1 layer prime coat and 1 layer jotashield paint to 100mm thk x 750mm (W) X 1.8m Length Motorcyle parking bay manually. | NEW | nos | 510 | 28 | 14280 | 510 | 23 | 11730 | 510 | 27.91 | 14234.1
Costing
Production: 1 day/ house/7 unit
Method: Manually
1.0 Manpower
1.1 Skill worker @ RM 70.00/day x 2= RM 140/day/ 7 nos
2. Material
2.1: Undercoat @ RM 6.93/litre x 3 litre= RM 20.70/ 7 nos
2.2 Jotasield @ RM 11.56/ litre x 3 litre = RM 34.69/ 7 nos
Hence total: RM 195.39/ 7 nos
1 no: RM 27.91
Sub-con quoted RM 27.91/nos
Discount RM 2.00/nos
Final rate RM 23.00/ nos
Other info
Thermoplastic painting
On premix RM 15/nos, 1 layer
On Concrete RM 25/nos, cause need to pain 2 layer
Prepare and apply one coat of sealer and two coats finishes weathershield to plastered surface to
5 | TNB External fence Wall | NEW | m2 | 494.13 | 7.37 | 3641.7381 | 494.13 | 5.85 | 2890.6605 | 494.13 | 5.85 | 2890.6605
6 | Handicap logo | NEW | no | 68 | 144.3 | 9812.4 | 68 | 130 | 8840 | 68 | 130 | 8840
| Total Phase 1 |  |  |  |  | 32884.7709 |  |  | 28232.2205 |  |  | 30736.3205
Phase 2
Building
Prepare and apply one coat of sealer and two coats finishes weathershield to plastered surface to
1 | MS door to House Unit rear door | NEW | m2 | 166.32 | 7.37 | 1225.7784 | 166.32 | 5.5 | 914.76 | 166.32 | 5.5 | 914.76
Prepare and apply one coat of primer and two coats of general surfaces of metal door frame
2 | MS door frame to House Unit rear door | NEW | M | 224.4 | 2.86 | 641.784 | 224.4 | 3.8 | 852.72 | 224.4 | 3.8 | 852.72
Prepare and apply one coat of primer and two coats of general surfaces of metal door frame
3 | House unit cantilever roof | NEW | no | 44 | 33.3 | 1465.2 | 44 | 30 | 1320 | 44 | 30 | 1320
External Works
4 | Lay 1 layer prime coat and 1 layer jotashield paint to 100mm thk x 750mm (W) X 1.8m Length Motorcyle parking bay manually. | NEW | nos | 334 | 28 | 9352 | 334 | 23 | 7682 | 334 | 27.91 | 9321.94
Costing
Production: 1 day/ house/7 unit
Method: Manually
1.0 Manpower
1.1 Skill worker @ RM 70.00/day x 2= RM 140/day/ 7 nos
2. Material
2.1: Undercoat @ RM 6.93/litre x 3 litre= RM 20.70/ 7 nos
2.2 Jotasield @ RM 11.56/ litre x 3 litre = RM 34.69/ 7 nos
Hence total: RM 195.39/ 7 nos
1 no: RM 27.91
Sub-con quoted RM 27.91/nos
Discount RM 2.00/nos
Final rate RM 23.00/ nos
Other info
Thermoplastic painting
On premix RM 15/nos, 1 layer
On Concrete RM 25/nos, cause need to pain 2 layer
Prepare and apply one coat of sealer and two coats finishes weathershield to plastered surface to
5 | TNB External fence Wall | NEW | m2 | 0 | 7.37 | 0 | 0 | 5.85 | 0 | 0 | 5.85 | 0
6 | Handicap logo | NEW | no | 44 | 144.3 | 6349.2 | 44 | 130 | 5720 | 44 | 130 | 5720
| Total Phase 2 |  |  |  |  | 19033.9624 |  |  | 16489.48 |  |  | 18129.42
| Total Amount (RM) |  |  |  |  | 51918.7333 |  |  | 44721.7005 |  |  | 48865.7405
7197.0328
13.86%